## Action Points
Action Point No. | Date Raised | Description | Progress | Owner | Status | Last Updated/ Date Closed
AP01 | 2011-11-02 | LG to create Yr. Planner and to circulate to KC to ensure no conflicts with School Calendar. | Year Planner created, distributed to school and KC has advised of some possible conflicts of dates. Year Planner v2. | Lisa Greenway | Completed | Completed
AP02 | 2011-11-02 | KC to investigate if it is possible to have PTA meetings etc. loaded in to School Website. | KC advises that all PTA material would need to come into school for approval by Mrs Yates. Once content agreed would be uploaded to school website by Miss Jenkins | Kirsty Cullen | Completed | Completed
AP03 | 2011-11-02 | KC to investigate if PTA can have access to Group Texting sent by School Office | KC confirmed PTA can have access to Group Texting to Parents for specific events/information | Kirsty Cullen | Completed | Completed
AP04a | 2012-01-11 | Food Evening. PTA insurance cover using camping stoves on School Premises | 14/03/12 Insurance documentation passed to Sarah Perks 18/04/12 Using electric stoves. AP no longer applicable | Sarah Perks | Withdrawn | 2012-04-01
AP04b | 2012-01-11 | Food Evening. Availability of School Hall or Children's Centre & Andy Clarke | Andy Clarke preference School Hall, however depends on number of tickets sold. | Kirsty Cullen | Completed | 2012-02-01
AP04b.1 | 2012-03-14 | Food Evening. Andy Clarke raised concern that this is now Joy Brewer's (office) leaving party. Alternative date suggested Friday 11th May - KC to check date and confirm ok to change. | School confirmed ok to change date | Kirsty Cullen | Completed | 2012-03-01
AP04c | 2012-01-11 | Food Evening. Can Lisa Middleton use school kitchen | Lisa confirms only requires access to small oven (warming food prepared earlier) and washing up facilities. Andy C asked that Lisa speaks to him personally. AP transferred to Lisa Middleton | Kirsty Cullen Lisa Middleton | Completed Completed | Feb-12 Apr-12
AP05a | 2012-01-11 | Quiz Night – New Parents needed to run event, action to promote interest in next Newsletter | Maria Hewitt and Alistair Burns have stepped forward as new volunteers to organise next Quiz event. | Julie Ellis | Completed | 2012-02-01
AP05b | 2012-01-11 | Disco - New Parents needed to run event, action to promote interest in next Newsletter by Julie Ellis and Becky Stephens to write to existing Disco helpers | JE included note on February PTA Newsletter BS sent email to Disco Helpers | Julie Ellis Becky Stephens | Completed Completed | Feb-12 12/03/2012
AP05b.1 | 2012-03-14 | Disco - New Parents needed to run event, action to promote interest in next Newsletter by Julie Ellis and Becky Stephens to write to existing Disco helpers | Karen Billington confirmed that 2 mums have expressed an interest in taking on some responsibilities relating to Disco. Laura Donahoe and Kim Crooke. Karen to establish what level of organising they are prepared to take on. 18/04 Karen confirmed that Laura happy to issue tickets. Kim's situation has changed, no longer able to consider taking on extra responsibilities. Jackie Archer, wants to get a better understanding of time/effort required to head up Disco's so has offered to job shadow Karen when she organises the next disco. Jul-12 Neither Jackie or Laura available to job shadow Karen at the Summer Disco. Sep12. Mtg to be arranged to go through steps taken to deliver event. Oct-12 Jacqui Archers husband explained that timing of event very difficult for Jacqui due to commitments with work Nov-12 Agreement reached whereby Karen to continue with Lead role for Christmas Disco with Laura Job Shadowing, Easter Disco roles to be reversed. Feb-13 Karen confirmed "Happy to let go", prepared to help with any of the tasks that Laura unable to complete. Laura has handover pack, with activities to be completed and timescales. Suggestion by Sarah Perks to facilitate the "hand over" by identifying which activities Laura able to do and those that Karen will continue to fulfil i.e. ordering of craft, booking of DJ. Mar-13 PTFA Committee agreed that unable to proceed with the Easter Disco, more parent helpers needed to supporting the organisers, delivering the event. May-13 Julie, Paul, John and David have come forward as team to take on Organisation of the Disco. Job Description to be sent out by Karen Billington Jul-13 New committee invited to job Shadow Karen on last disco of the year. Sep - New committee has met up and allocated key roles to individuals | Karen Billington | Completed | 2013-09-01
AP05c | 2012-01-11 | Christmas Fayre- New Parents needed to run event, action to promote interest in next Newsletter | Julie asked those committee members present at the Mtg 260912 if anyone would be willing to lead a team to deliver this event. No volunteers. 31/10/12 Nadia Baxter has volunteered to deliver the Christmas Fayre and on a temporary basis to stand in as Chair of the PTA up to this event. 21/11/12 Nadia gave an overview of the tasks she had so far completed or had in hand. Everything going to plan, despite the very short timescales | Nadia Baxter | Completed | 2012-12-01
AP06 | 2012-01-11 | School Recipes – request for Anna to publish on school website and ability to use Blog. | KC spoken to Anna, who is very flattered but doesn't have time to collate info. KC will speak again in Autumn | Kirsty Cullen | Completed | Feb-12
AP07 | 2012-01-11 | Establish the type of Injury’s (seriousness) that should be reported and recorded on PTA-UK incident report. | Only incidents where casualty requires professional medical attendance i.e. paramedics or taken to hospital | Lisa Greenway | Completed | Feb-12
AP08 | 2012-02-22 | Lisa Middleton to confirm if she is still able to host Food Event on 27/04/2012 | Yes, however change of date proposed. | Lisa Middleton | Completed | 2012-03-01
AP09 | 2012-02-22 | Temp Event Notice to be processed for Disco 23/03/12 | Lisa has applied for Temp Event Notices 23/3/12 and 13/07/12 | Lisa Greenway | Completed | 2012-03-01
AP10 | 2012-02-22 | Lisa Greenway to provide Lisa Middleton with overview of Fun Run Event, to establish if husband willing to take on shared responsibility | Lisa M' husband doesn't have spare time currently to support this event. | Lisa Middleton | Completed | 2012-03-01
AP10a | 2012-03-14 | Fun Run - suggestion to defer and consider running event in October. Kirsty Cullen to put this to school and come up with a potential date and availability of staff to support. | Kirsty has approached staff at school. Teachers happy to support event, but don't want to organise. Concerned that weather in October might not be favourable, preference would be April/May. Lisa Greenway advised that May is difficult month for her. | Kirsty Cullen | Completed | 2012-04-01
AP11 | 2012-02-22 | Summer Fayre - Olympic Theme Create Olympic Torch each class, judged and prize | In principle KC confirms school would be willing to support, however too early to start preparing etc. This request did not materialise. | Kirsty Cullen | Withdrawn | 2012-03-01
AP12 | 2012-02-22 | Summer Fayre - Balloon Release (ECO friendly tags | No progress. This was not pursued | Lisa Greenway | Withdrawn | 2012-06-01
AP13 | 2012-02-22 | Summer Fayre - Raffle Prize Letter | Julie confirmed that she had prepared 130 letters to local business's asking for prizes. Needs envelopes and stamps. Karen and Natalie offered envelopes. | Julie Ellis | Completed | 2012-04-01
AP14 | 2012-02-22 | Can School produce DVD (minimal cost)for parents to purchase of School Events? | short Answer No, so many different Parent Preferences i.e. have to give approval to pictures, website, newspaper. That extremely difficult to manage in practice. Mr Russell has however agreed to take pictures of PTA events and once content reviewed show them on school website. | Kirsty Cullen | Completed | 2012-03-01
AP15 | 2012-03-14 | Kirsty Cullen to ask school to consider supporting Fun Run in October. To check whereabouts of Head / Deputy Head etc. | 26/09/12 School's view updated and closed on AP to 10A. Suggestion from school to continue to deliver Event in May. However, May is not a good time for the organisers. 16/01/13 June 9th Proposed, Wtg for School to confirm ok to proceed 15/05/13 Cancelled due to lack of participants to prepare the activity. Joint Venture with Maney Hill considered but rejected due to timing and feasibility. | Kirsty Cullen | Cancelled | 2013-05-01
AP16a | 2012-03-14 | Deanery Does Ready Steady Cook - Temp Event Notice Required, once date confirmed | Application form submitted to BCC Licensing & Police | Lisa Greenway | Completed | 2012-04-01
AP16b | 2012-03-14 | Deanery Does Ready Steady Cook - Lisa M will need a small number of volunteers to help her on the night will ask her own circle of friends first | Lisa sourced own volunteers | Lisa Middleton | Completed | 2012-04-01
AP16c | 2012-03-14 | Deanery Does Ready Steady Cook - Hold the Date in your diary to be entered in to next PTA newsletter | Julie included in PTA Newsletter | Julie Ellis | Completed | 2012-04-01
AP16d | 2012-03-14 | Deanery Does Ready Steady Cook - Quiz Master Required | Julie confirmed that Karen Taylor's dad had volunteered to be Quiz Master at the March Quiz if Noel was unavailable. Julie to approach Karen. Lisa Middleton hosted her own quiz | Committee | Completed | 2012-05-01
AP16e | 2012-03-14 | Deanery Does Ready Steady Cook - Lisa M to create flyer for distribution with next PTA newsletter | Lisa has produced poster and sent in copy for committee to see. Great, colourful and informative. Copies to be sent into school. Natalie will use content and create flyer for parents to request tickets | Lisa Middleton Natalie Lockrey | Completed Completed | 2012-04-01
AP17 | 2012-03-14 | Disco - Committee agreed that we should book Next School Year Disco's in advance. Friday before the last week in half term. Once booked dates to be forwarded to School Office for inclusion in school calendar. | Karen Billington confirmed that the most popular DJ's are booked up many months in advance. Will pursue and also ensure Yr. 6 leavers disco booked (19th July). | Karen Billington | Completed | 2012-04-01
AP18 | 2012-03-14 | Fashion Show- Committee to find suitable venue to hold this event, Saturday afternoon 2-5pm, 3-6pm. | Andy Clarke advises that both school hall's rented out until 6pm Saturdays. Lisa Greenway has checked with Walmley Social Club, restricted by evening entertainment. Have Sat 23rd June available. £100.00 refundable deposit. St Johns Church would be a great venue. Lisa Greenway has spoken to church office and checked availability. Free Sat 19th May, Sat 1st, 9th & 30th June. Wtg confirmation that able to use church for non ceremony event. Church confirmed OK, however church family member must be present i.e. Mrs Rose, cost £50.00 per hour. 18/04 Julie advised not yet been able to establish if company work on Saturdays. Jun-12. Unable to spend further time on this activity due to concentrating on Summer Fayre. Sep-12 request from committee to provide details just in case someone wants to run this event this year. Oct-13 Sean to send out a request via Newsletter asking if any parent(s) would like to take on this event Jan-14 Agreed to cancel as No Action taken since June-12 | Sean Sterling | Cancelled | 2013-10-01
AP19 | 2012-03-14 | Uncle Zoobee - Lisa Greenway to contact Shane and confirm his availability to run an event for Nursery & Reception children | Shane unable to accommodate PTA preferred date of Fri 12th Oct. Can offer only 2 dates around this time Fri 28th Sept or Fri 9th Nov. School Office confirmed that all Nursery Children will be in school full-time by 28th Sept. Date booked. Lisa to confirm event details / prices with Shane Event booked for 28/09/12. 5:00 - 6:35 18/04 Julie confirmed that event duration was 1.30 mins (5pm-6:30pm), believes 2 x 40 min shows (magic show & puppet show) with 20 minute break for refreshments. Price included balloon for each child. From memory believe 120 children attended. Julie has copies of poster and flyer from previous event. Lisa to confirm with Shane the cost for the event. | Lisa Greenway | Completed | 2012-04-01
AP20 | 2012-03-14 | Teddy Bear Picnic Events - PTA representatives required to be present at the event to encourage new parents to join us and answer any questions. Request for volunteers to go out via Email. | 18/04 Julie to check her files to see if she has kept a copy of the letter that went out with Nursery Induction Packs. Kirsty confirmed dates as 25th/26th June. Email to PTA asking for additional reps to attend on the day. Natalie will be attending. Julie attended 1st but not 2nd due to own child being poorly. | Julie Ellis | Completed | 2012-06-01
AP21 | 2012-04-18 | Deanery Does Ready Steady Cook - PA System will need to be available and up and running. Kirsty to speak to Andy Clarke | KC has passed information onto Andy Clarke. | Kirsty Cullen | Completed | 2012-05-01
AP22a | 2012-04-18 | Uncle Zoobee - Karen to approach Laura Donahoe to see if she will issue tickets. | Due to time constraints, Laura was not approached on this occasion, Karen offered to complete the task herself | Karen Billington | Completed | 2012-09-01
AP22b | 2012-04-18 | Uncle Zoobee - Natalie to approach Debbie Weller to see if she would be willing to take this on. Based on previous event need Lead + 6 people to help with refreshments | Unfortunately Debi was celebrating a special birthday this month and it was decided not to ask her. Lisa assumed responsibility for event | Natalie Lockrey | Completed | 2012-09-01
AP23a | 2012-04-18 | Father's Day Hamper - Natalie to create flyer with plenty of suggestions and try to get copied and distributed to children this week. | Discussion and recognition that this will be more difficult for parents to participate in, however, we should trial. Key to success giving parents plenty of notice to purchase / obtain Dad's gift. Father's Day Sunday 17th June. Will need children to bring in gifts by 1st June. | Natalie Lockrey | Completed | 2012-05-01
AP23b | 2012-04-18 | Mother's Day & Father's Day Hampers Event - Natalie to produce a fact file of what she did, when, how many helpers etc., so next year another parent volunteer could take this on. | Feb-13 Natalie reminded that AP outstanding Oct-13 Agreed that once template created to sit down with Natalie and capture relevant information for these 2 events | Natalie Lockrey Rebecca Riddell | Completed | 2014-03-01
AP24 | 2012-04-18 | Facebook - Kirsty to confirm view of School in respect to creating a Facebook page for PTA | 12/10 Management team not happy about having pita Facebook page | Kirsty Cullen | Completed | 2012-10-01
AP25 | 2012-04-18 | Christmas Sleigh - Kirsty to establish size and whether it can be stored on school premises. | School investigated but confirmed that too large to store on school premises. | Kirsty Cullen | Completed | 2012-09-01
AP26a | 2012-09-26 | Forthcoming Events - 1st Term. Quiz, Disco, Christmas Fayre. Lisa to populate into Year Planner and apply for Temp Event Notices from BCC. | Year Planner created, Temp Event Notices applied for. | Lisa Greenway | Completed | 2012-10-01
AP26b | 2012-09-26 | Kirsty Cullen to ask school to confirm dates and populate into School Diary. | Issue with Christmas Fayre. New date proposed Friday 7th December. PTA agreed to new date. New date required new temp event notice, completed by Sarah Perks | Kirsty Cullen | Completed | 2012-11-01
AP27 | 2012-09-26 | PTA Chair. Julie Ellis to prepare 1 page summary outlining the role and responsibilities of PTA chair. To be distributed before the AGM | Not completed | Julie Ellis | Withdrawn | 2013-02-01
AP28 | 2012-09-26 | PTA funds profile. Sarah was asked to prepare a page dedicated to PTA Funds that could be sent out to all parents of our school. To include a. Registered Charity b. Matched Funding or similar c. Amount held in bank d. Total made for last school year e. Amount donated to individual external Charities | Feb-13 Sarah reminded that AP outstanding Mar-13. Sarah brought to the meeting draft for review and approval. Shows Donations To School, Donations to other charities, Monies Raised and Total Funds available in bank. All agreed excellent doc, should go out to all parents in paper format ASAP and be uploaded on School website. | Sarah Perks | Completed | 2013-03-01
AP29 | 2012-09-26 | Nursery Christmas Event. Kirsty asked to explore with School if they would like the PTA to pay for an entertainer or trip out specifically for Nursery Children as they are the only group not attending the Pantomime at Lichfield Garrick Theatre. | Kirsty advised that they had approached Creation Station, Wtg quotation for session. Nursery Event Booked, cheque's written for deposit and outstanding balance. | Kirsty Cullen | Completed | 2013-02-01
AP30 | 2012-09-26 | School Council Kirsty was asked to explore with School Council any Funding Ideas from the children | 12/10 the school council is looking at outdoor learning areas - the children have all voted for their representative and they meet next week - first topic is playgrounds 21/11 Nadia confirmed that 3 requests for funding had been made via the School Council. Please see separate sheet for details of request. Oct-13 Email sent to Jill Sharp asking for Agenda Item on next School Council meeting. Jan-14 Email from Jill to advise that she is the Lead Teacher for School Council. She has agreed to make them aware of the PTFA and will feedback any ideas that they have. | Jill Sharp | Completed | 2014-01-01
AP31 | 2012-10-17 | Quiz Night - Consider running a Bar to use up left over stock of Beer and Wine not used at the Summer Fayre | 17/10 Natalie to discuss with Maria Hewett Feedback from Maria, alcohol did not sell very well, with majority of people bringing their own. | Natalie Lockrey | Completed | 2012-11-01
AP32 | 2012-11-21 | Change of approved Signatures on PTA Cheques. Essential to update the names of approvers to Sean Stirling (Chair) Sarah Perks (treasurer) Lisa Greenway (secretary) | 21/11 Sarah to investigate process and pursue Dec-12. Julie Ellis, Jane Shingler, Karen Taylor and Becky Stephens removed from a/c. New committee members added | Sarah Perks | Completed | 2012-12-01
AP33 | 2012-11-21 | Website to be updated to reflect Current Committee | 21/11 Sean to prepare a new "introduction to the Deanery PTFA" and forward on to school. | Sean Sterling | Completed | 2013-02-01
AP34 | 2012-11-21 | Updated Contact List for Deanery Parents | 21/11 Lisa to prepare current list, incl attendees of Nov Mtg and Sean to include opt in/out to PTA on next PTFA newsletter, also to consider following up with Group Text. | Lisa Greenway | Completed | 2013-01-01
AP35 | 2013-01-16 | Recognition | 16/01/13 Sean to recognise Nadia for her hard work and very successful Christmas Event. Agreed Recognition should be flowers and presented in School Assembly. 13/03/13 Sean confirmed everything in hand for 15/03/13 | Sean Sterling | Completed | 2013-03-01
AP36 | 2013-01-16 | Event Dates | 16/01/13 Kirsty to confirm if provisional dates for meetings and events agreeable with school. 27/02/13 Sean confirmed he had not received any concerns from school over the dates proposed. Action closed | Kirsty Cullen | Completed | 2013-02-01
AP37 | 2013-01-16 | Forthcoming Events - Organisers | 16/01/13 Lisa to contact “mums” below to see if they will organise these events again this year. Maria Hewitt (Quiz), Natalie Lockrey (Hampers), Lisa Middleton (Food Event). Everyone said "yes", month to be agreed with Lisa | Lisa Greenway | Completed | 2013-02-01
AP38 | 2013-01-16 | Fireworks Event | 16/01/13 David Archer confirmed that he would contact Maney Hill PTA and gain understanding of this event and whether its possible to deliver similar event at the Deanery 27/02/13 Update from David, Maney Hill looked at 2 options to deliver this annual event 1) Hire Company who "run" the fireworks event, 2) Parents completed training programme and obtained the necessary license. Option 2 cheaper. Format of Maney Hill Event, Bonfire, Fireworks and Refreshments - aimed at families with young children. Attendance in the region of 400 people. Andy Clarke has been approached and is willing to consider the PTA putting on this type of event. Number of things to be explored. a) BCC Licensing (Lisa) b) PTA Insurance (Sarah) c) St Johns Ambulance Service? d) Dates of other similar events (David) e) Use of toilets either in School or Children's Centre (Shaun) f) Cost to Hire Companies (David) Karen confirmed she may know someone who holds this type of license. Mar-13 Sarah has sent some information out from the National PTA Facebook page with details of prices and companies who host this type of event. Mar-13 Lisa has sent to David and Sean information sourced by the Fire Safety Team. Mar-13 Sarah made a suggestion that we could approach Maney Hill to see if we could sell tickets to the Deanery parents to attend their event and take a cut of the ticket sales? AP 45 Sarah to contact Maney and explore if possibility, to also consider Fun Run. MAy-13 This has been cancelled due to creating damage to field and competing against established events. | David Archer | Cancelled | 2013-05-01
AP39 | 2013-01-16 | March Disco - Parent Helpers required to set-up | 16/01/13 Sean to contact Laura Donohue to obtain relevant details for newsletter 27/02/13 Karen confirmed that she will be available to "set up" the disco. | Sean Sterling | Withdrawn | 2013-02-01
AP40 | 2013-01-16 | Charities Website - Out of Date Trustee Information | 16/01/13 Committee advised that website out-of-date showing Parents who have left the Deanery | Lisa Greenway | Completed | 2013-02-01
AP41 | 2013-01-16 | Welcome PTA letters that go out with School Induction Packs etc. to be updated by New chair | 16/01/13 Sean to establish with school office which documentation includes PTA Welcome letter. Oct-13 Sean had completed but out-of-date again. Some minor tweaks required. Jan-14 Rebecca will update document, also to include information ref Second Hand School Uniform for N,Yr1 Mar-14 Jill to confirm when this document will be distributed to new parents. Apr-14 Distribution to new parents May 9th May-14 welcome letters circulated | Rebecca Riddell Jill Sharp Lisa Greenway | Completed | 2014-05-01
AP42 | 2013-02-27 | Job Description Template | 27/02/13 Sarah to create a blank template that can be used to identify specific roles that need a parent volunteer to fulfil, i.e. stand-alone activity i.e. issuing tickets for all events or a specific task, running a stall at the Summer Fayre 13/03/13 Sarah confirmed draft created, will have final copy for issue for next meeting. 01/2014 Rebecca has downloaded the PTA Job Descriptions, Lisa to prepare draft for each of the Elected Member Roles - Chair, Treasurer and Secretary plus Sub Committee and Ordinary Members 25/01/14 Lisa pulled together 1 page document for each of the Job Descriptions and circulated to each Elected Members to review, amend and agree. 09/02/14 Bex has reviewed and merged documents - final sign off required 30/04/14 Bex and Lisa reviewed again, Natalie and Michelle to sign off document 08/05/14 Content agreed, Lisa to send to Kirsty Cullen to ask for upload to website | Officers | Completed | 2014-05-01
AP43 | 2013-02-27 | Temp Event Notices | 27/02/13 Lisa Greenway to deal with forthcoming events 2 Disco's, Comedy Night 13/03/13 No requirement for Event notice for Easter Disco as event cancelled. 15/05/13 No requirement for Event notice for Comedy Night as event cancelled. 19/06/13 Temp event Notice to be requested by w/c 24/6/13 | Lisa Greenway | Completed | 2013-06-01
AP44 | 2013-02-27 | Passport Size Photos | 27/02/13 Mrs Yates has requested photo of Chair, Treasurer and Secretary for School Notice Board 13/03/13 Sean asked that Photo's be available for April Mtg Oct-13 Both Lisa and Rebecca confirmed that they would not be happy to have their Photo's on display. Sean to provide photo if he's happy to do so | Sean Sterling Sarah Perks Lisa Greenway | Withdrawn | 2013-10-01
AP45 | 2013-03-13 | Maney Hill - Fun Run / Firework Event | Sarah to contact Maney Hill School and explore if possible to join up with them for their Firework Event and Fun Run and come to some agreement of contributing to event and taking ticket sales etc. 15/05/13 Participants at meeting agreed not to pursue. | Sarah Perks | Cancelled | 2013-03-01
AP46 | 2013-03-13 | School Term Dates Document to include PTFA events | Kirsty to ask for School Term dates document to be re-issued to include PTA Events. Oct-13 Email to Jill Sharp asking for confirmation that will be completed for all future events | Jill Sharp | Completed | 2013-10-01
AP47 | 2013-03-13 | Personal Contact to PTFA parents | Sean to write to all parents who attended Oct AGM and all those people who have given us their email contact details asking for support and attendance at PTA meetings. Oct-13 Not Completed | Sean Sterling | Withdrawn | 2013-10-01
AP48 | 2013-03-13 | Learn Pad questions | Paul Lord to collate questions/concerns regarding the Funding request of 30 Learnpad tablets, to be sent to Kirsty before the next meeting giving Mr Russell sufficient time to review and respond. | Paul Lord | Completed | 2013-04-01
AP49 | 2013-03-13 | Notification of parents of Funding Request £8300 | Sarah to include on PTFA Finance Update invitation to all Parents to come along to the next Mtg 17th April and discuss Mr Russell's request to spend £8300 of PTFA funds on 30 Learn pad tablets. | Sarah Perks | Completed | 2013-04-01
AP50 | 2013-03-13 | Placement of 3rd Noticeboard | Sarah to spk to Mrs Yates and agree location of 3rd PTFA noticeboard in/around Children’s Centre. Oct-13 Sarah still has supplier details, Natalie has spoken to Mrs Yates who has confirmed that she's happy to have noticeboard on the fence as you walk into KS1 playground, also suggested that we could use the existing one on the corner of year 1. Leave in situ or relocate. Jan-14 All agreed that we will use the existing one in the school playground and try to establish the impact of it by putting something in the noticeboard that can measure it's usefulness. | Sarah Perks Sean Sterling | Completed | 2014-01-01
AP51 | 2013-03-13 | Use of freeze board in school for PTFA information | Natalie to speak with Mrs Yates and request use of the noticeboard next to school admin office (internal) for PTFA information. Oct-13 Agreed need to speak to Natalie at the next PTFA meeting to ascertain if this is still a viable option and if needed? Jan-14 Natalie confirmed that the location of freeze board that has been offered is not in a great location and will not get the parental exposure needed to make the time and effort of creating and updating a display worthwhile. Idea ditched. | Natalie Lockrey | Cancelled | 2014-01-01
AP52 | 2013-04-17 | Comedy Night - possible use of school hall | Kirsty to check with school that one of the halls could be used for Comedy Night May-13 Comedy Night cancelled due to insufficient tickets being sold. | Kirsty Cullen | Cancelled | 2013-04-01
AP53 | 2013-04-17 | Comedy Night - Lisa Middleton providing nibbles | Lisa to speak to Lisa Middleton ref providing nibbles for Comedy Night Apr-13 Lisa happy to support May-13 Event cancelled due to lack of parental support | Lisa Greenway | Cancelled | 2013-04-01
AP54 | 2013-04-17 | Comedy Night - Children's Centre | Lisa to contact Jackie Darcy ref not using Children’s Centre Apr-13 Completed May-13 Event cancelled due to lack of parental support | Lisa Greenway | Cancelled | 2013-04-01
AP55 | 2013-04-17 | Summer Fayre - Organiser | Kirsty to ask member of staff if they would take Lead role of organising Summer Fayre May-13 Natalie Lockrey has put herself forward to Organise the Summer Fayre | Kirsty Cullen | Completed | 2013-05-01
AP56 | 2013-04-17 | PTFA Contact List | Lisa to send Julie the current PTFA Contact List | Lisa Greenway | Completed | 2013-04-01
AP57 | 2013-05-15 | Freeze Pop Friday | PTFA Committee to purchase Freeze Pops on behalf of year 6. Profits to be another opportunity to "give" to external charities. | Lisa Greenway | Completed | 2013-06-01
AP58 | 2013-05-15 | PTA Constitution | Due to the resent voting issue affecting “Learn Pads” it was suggested by Julie that we should ensure everyone has a clear understanding of the PTA constitution (including trustee’s expectation) to ensure no infringement s being made during future PTFA meetings. Lisa to find suitable document for circulation at next Mtg and should be available via school website. Oct-13 discussion ref where Constitution held, Rebecca believes on Charities commission website. To print-off and a separate meeting Sean, Rebecca and Lisa to discuss and check understanding of content. Jan-14 Bex confirmed that she has obtained a copy of the Constitution and signed it and uploaded to Charities Commission website (standard version with no deviations). 25/01/14 Lisa has reviewed formal documentation and extracted key information that would be relevant to our members 09/02/14 Bex has merged information with R&R etc. - final sign off required 30/04/14 Natalie and Michelle to sign off document 08/05/14 Lisa to send copy to Kirsty Cullen for upload to Website | Officers | Completed | 2014-04-08
AP59 | 2013-05-15 | Nursery/Reception Induction Evening | Natalie to confirm on Monday 20th May the date for 2013 – 14 class-year induction evening. PTFA representative will talk reception/nursery parents about the PTFA opportunities within the association. Sean has highlighted his interest to be involved with this event. | Sean Sterling | Completed | 2013-05-01
AP60 | 2013-07-17 | First Aiders | Lisa asked to compile list of all parents & friends who currently have a valid first Aid Certificate, list to be distributed to Disco Organisers. Oct-13 Whilst bringing the PTFA contact list up-to-date Rebecca will also ask parents if they are current First Aiders Jan-14 To be included in Jan newsletter 11/02/14 Only 4 Returns received from parents outside those that normally attend meetings, none of them accredited First Aiders - to be picked up again at next meeting. 11/03/14 Action transferred to Michelle, to identify the names of those parents who participated in PTFA paid for course held at the Children's Centre 08/05/14 Michelle has a found the receipt but participants not identified. Agreed no ability to take this further. | Michelle Dolphin | Closed | 2014-05-01
AP61 | 2013-10-01 | Film Night | Debra Corkwell has suggested that PTFA could introduce Film Night, She's happy to help organise. Kirsty to check with School ref Licences. | Kirsty Cullen | Completed | 2014-01-01
AP62 | 2013-10-01 | Film Night | Debra to speak to Helen Kent ref the existing Film club to ensure she's happy with us considering this as an event and to glean additional info | Debra Corkwell | Completed | 2014-01-01
AP63 | 2013-10-01 | PTFA Year Planner | All parents present at the meeting reviewed the draft proposed dates. Amendments made as per discussion. Lisa to send to school and confirm ok to proceed. | Lisa Greenway | Completed | 2013-10-01
AP64 | 2013-10-01 | Ready Steady Cook | Proposed date Fri 31st Jan. Lisa Greenway to confirm with Lisa Middleton that this is ok with her. Lisa confirmed date OK | Lisa Greenway | Completed | 2013-12-01
AP65 | 2013-10-01 | Summer Ball | Rachael to send out flyer to all parents to ascertain take-up numbers who would support this event and indication of cost per person to participate. | Rachael Smith | Completed | 2013-10-01
AP66 | 2013-11-26 | Existing Funding Requests | Lisa to send information to Jill ref the 2 existing suggestions made for funding opportunities. | Lisa Greenway | Withdrawn | 2013-11-01
AP67 | 2013-11-26 | Resubmission of Funding Requests | Jill was asked to resubmit 2 new funding requests on the new template. Mrs Johansson has withdrew her request only Nursery Event re-submitted | Jill Sharp | Completed | 2013-12-01
AP68 | 2013-11-26 | Enterprise Challenge - Award | Jill Sharp to ask Miss Morris if the PTFA could purchase a trophy for winning team of the Enterprise Challenge. Miss Morris felt that individual recognition more appropriate i.e. vouchers than team trophy. | Jill Sharp | Completed | 2013-11-01
AP69 | 2013-11-26 | Nursery Christmas Event | Jill Sharp to ask Nursery teachers to investigate and come back to PTFA with options up to £240.00 maximum contribution towards Christmas event. Mrs Brown has sourced an appropriate event - £200.00 | Jill Sharp | Completed | 2013-11-01
AP70 | 2013-11-26 | Enterprise Challenge - float requirements | Jill Sharp to ask Yr6 teachers to come back with float requirements for the Yr6 Enterprise Challenge. Float requirements given to Michelle | Jill Sharp | Completed | 2013-11-01
AP71 | 2013-12-10 | Disco Committee - Stock take | Disco committee to complete a stock take and report findings to Michelle Jan-14 Stock-take completed and information forwarded to Michelle | Disco Committee | Completed | 2014-01-01
AP72 | 2013-12-10 | Christmas Fayre - Events Template | Christmas Fayre Committee to update and record all steps taken to deliver event on new Events Template. 08/04/14 Bex confirms bulk of data recorded, final tidying up of document required 08/05/14 Content approved. 15/09/14 added in documents. Email to Michelle waiting for receipts so can update quantities ordered for food etc. Also need copy of fire evac procedure. Jan'15 Bex to add this years refreshments list to template. | Christmas Fayre Committee | Completed | 2015-01-01
AP73 | 2013-12-10 | Minimum Bank Account Balance | Michelle to review historic accounts and suggest minimum amount required in bank account by monthly timeline. 08/05/14 Agreed that it would be easier is the Treasurer was asked to provide a current bank balance at every meeting. Michelle agreed happy to provide | Michelle Dolphin | Closed | 2014-05-01
AP74 | 2014-01-14 | Amendment to Funding Request Template | Funding request template to be amended to include “Outside of school budgets” | Rebecca Riddell | Completed | 2014-01-01
AP75 | 2014-01-14 | whole or Part contribution to Sound & Light system and floor covering around outdoor KS2 gym equipment | Jill to establish, If Sound & Light system and floor covering to be purchased this school year? And if PTFA unable to provide whole funding will contribution be OK and to what value? Mrs Yates would like to purchase both items this school year. If she decides to ask the PTFA she will complete the funding request template. | Jill Sharp | Completed | 2014-01-01
AP76 | 2014-01-14 | Website to be updated to reflect Current Committee | Lisa to get PTFA website updated to reflect Natalie and Bex taken shared responsibility for Co Chair. Email sent to Jill Sharp | Lisa Greenway | Completed | 2014-01-01
AP77 | 2014-01-14 | Ready Steady Cook | Natalie to speak to Lisa M. ref Ready Steady Cook Agreed that due to personal commitments it would be beneficial to postpone event. Suggestion of new date of 28/03/14. Lisa and Andy C to confirm ok. Both parties agreed to proceed with this date | Natalie Lockrey | Completed | 2014-01-01
AP78 | 2014-01-14 | Request for Prizes | Bex to request prizes for Summer Ball and Fayre on next newsletter. | Rebecca Riddell | Completed | 2014-01-01
AP79 | 2014-01-14 | Re-issue of School dates for this term | Jill to investigate if school will re-issue Term Dates document with PTFA key dates included. Mrs Yates has agreed to re-issue document to include PTFA dates. 11/02/14 School will not re-issue dates but have sent out a separate letter. | Jill Sharp | Completed | 2014-02-01
AP80 | 2014-01-14 | PTFA paper newsletters | Jill to investigate if PTFA can continue to send out paper newsletters. Mrs Yates is intending to go fully paperless, therefore does not want the PTFA newsletter to go out in paper format. Happy for it to go on the website. Given that it includes contact request form would like Mrs Yates to re-consider. Jan newsletter printed and distributed in paper format | Jill Sharp | Completed | 2014-01-01
AP81 | 2014-01-14 | Reminder to parents of PTFA area of school website | Lisa to send Jill a statement that advises PTFA have their own area of the website and this is where they can find info on events, meeting dates. Reminder to be included on school newsletter. Nicky (school office) will include reminder | Jill Sharp | Completed | 2014-01-01
AP82 | 2014-01-14 | Use of School records of parents email addresses | Suggestion to ask Mrs Yates if we can ask parents if they give us permission we can have access to school records of parents email contact details. 11/02/14 Mrs Yates cannot agree to this request. | Natalie Lockrey | Completed | 2014-01-01
AP 82 | 2014-01-14 | School Governors | Committee to investigate how they can establish a relationship with the governors of the school. Natalie to speak to Marcia Squire-Wood to see if she would like to attend a PTFA meeting. 01/07 Agreed Natalie to call ahead and speak to Head of School Governors - Richard Petley, Bex to follow up with an email formally inviting Governors to attend AGM / regular PTFA meetings. 15/09/14 Need Richard Petley's email address. Also waiting on Natalie to make phone call. 16/09/14 Natalie text Richard and received positive response. 17/09/14 Kirsty emailed Richard list of pitta meeting dates. 11/02/15 Rachael Smith has been nominated as parent governor and now sits on both committee's. 12/05/15 Agreed that we should forward a copy of our Funding Document to Miss Ainsley for general distribution to school staff, managers and governors, also to hold a copy of our section of the web-site 14/04/15 Rachael has fed back that the Governors have mentioned purchasing a projector. More information needed - Rachael to ask the School Management Team to complete a PTFA funding request. 17/05/15 Rachael advised that as of the current date she has not attended a Full Governors Meeting - scheduled for 08/07/15 08/07/15 No update Rachael not present 03/02/16 Agreed that as Rachael both a PTFA Rep and a Parent Governor that gives us the 2-way communication path into Governors and vis-versa. | Rachael Smith | Closed | 2016-02-01
AP83 | 2014-02-11 | First Aid Kit - list of essential items | PTA Org has confirmed that for Insurance purposes there is not a “standard” first aid kit. Agreed we need someone in the medical profession to volunteer to come up with a list of essential items – Natalie suggested she might know someone who would be willing to do this for the PTFA. Liz Gunn has kindly offered to do this for us 26/02/14 Jill has confirmed that school happy to purchase additional items. PTFA to give Mrs Small (school office) list of items required. 11/03/14 Action transferred from Natalie to Liz. Request that Liz produces a check list in readiness for next event 28/03/14 and any missing items are itemised and given to Nicky (School office). | Liz Gunn | Completed | 2014-03-01
AP84 | 2014-02-11 | Nominated Role to check content of First Aid Kit before and after each event | Suggestion that we should have a nominated individual who is responsible for checking that we have a fully stocked FA kit, in readiness for each event. Natalie to ask friends. Liz Gunn has kindly agreed to take on this role | Natalie Lockrey | Completed | 2014-02-01
AP85 | 2014-02-11 | Accident Book | Lisa to purchase appropriate book to be used at all events. | Lisa Greenway | Completed | 2014-03-01
AP86 | 2014-02-11 | Disco 4th April - Teachers availability | Disco committee asked Mrs Sharp to ascertain if any teachers would be present at the next disco. Would be useful to know this information in advance. | Jill Sharp | Completed | 2014-03-01
AP87 | 2014-02-11 | Re-branded Promotional Documents for Quiz Night | Bex has worked her magic and updated all templates. Lisa to check with Quiz organiser Maria Hewett happy with content and forward to school office for printing and distribution Monday 24th Feb. Maria happy - Bex Sent into school office | Lisa Greenway | Completed | 2014-03-01
AP88 | 2014-02-11 | Quiz Night - Temp Event Notice | Lisa to apply for Temp Event Notice checked with PTA-Org TEN not required | Lisa Greenway | Completed | 2014-02-01
AP89 | 2014-02-11 | Ready Steady Cook (2nd Event) - promotional documents | No-one has previous documents, new ones to be created, Bex to source info from Lisa Middleton | Rebecca Riddell | Completed | 2014-02-01
AP90 | 2014-02-11 | Ready Steady Cook (2nd Event) - Temp Event Notice | Lisa to apply for Temp Event Notice | Lisa Greenway | Completed | 2014-02-01
AP91 | 2014-02-11 | Ready Steady Cook (2nd Event) - Location? | PTFA preference to use Children's Centre. Jill to ask school. 26/02/14. Jackie D has confirmed that they have just had all the carpets intensively cleaned ready for an inspection, because of this would prefer event to be located else where. School have suggested using newly furbished Craft Room. 06/03/14 Need to school to confirm max capacity of room for seated adults? 11/03/14 Venue agreed as "reception class" max 50 seated adults. | Jill Sharp | Completed | 2014-03-01
AP92 | 2014-02-11 | Correspondence - PTA.Org | PTA Org certificate of Insurance received, sent incorrectly FAO Julie Ellis. Lisa to ensure records updated | Lisa Greenway | Completed | 2014-02-01
AP93 | 2014-02-11 | PTFA Year Planner 2014- 2015 | Committee to produce Year Planner for 2014-2015 and send into school by end of June Feb Lisa has produced a draft copy - committee to review and make any amendments as necessary 01/05/14 Lisa has reviewed document and taken into consideration request to alternate PTFA monthly meetings between Tuesdays and Wednesdays, move Quiz from March to May, move Easter and July disco's so as not to clash with Sutton TKD Grading sessions (Impact on committee not being able to support disco helpers rota). Final review and sign off required. 08/05/14 Reviewed content and amendments made. copy to be printed off and sent into school for agreement. 10/06/14 Disco committee would like the Disco's returned to penultimate Friday before Easter and Summer Holidays and understand implication that some of committee members are unable to volunteer as Parent Helpers (particularly for KS2 when numbers are low) as their children are involved in TKD. 01/07/14 Request to send proposed Events, Dates and Times to Kirsty Cullen. 01/07/14 All dates agreed from school. Table Top Sale confirmed as Saturday rather than Friday. | Lisa Greenway | Completed | 2014-07-01
AP94 | 2014-02-11 | Alternative Contact for Andy Clarke | The committee asked who their point of contact in school would be if Andy C was on holiday, sick or simply not available to deal with a query. Action Jill 11/03/14 Should Andy not be available then it would be down to Mrs Yates to make alternative arrangements - likely to be Fred. | Jill Sharp | Completed | 2014-03-01
AP95 | 2014-02-11 | 2nd Hand Uniform - School and "other" organisations | Michelle to speak to Kate Davazadeh to ask if she would be willing to consider also receiving "other" unwanted or unused uniforms such as rainbows, scouts, brownies etc. 11/03/14 Action transferred from Michelle to Kate. Kate advised that she didn't think it was a good idea, with most parents automatically "passing on" unwanted, unused uniforms. The 2nd hand shop has been reduced to jumpers for Little Hollies Nursery, Reception and Yr1. The Jumpers are not wearing well for older years and the white shirts are so cheap to buy now from supermarkets that not worth selling. Kate has suggested that 2nd hand uniform shop should be promoted in Nursery Welcome Pack. Kate intends to be available at the Welcome Meetings. 08/05/14 Action to be deferred to New School Year, to be included in First Newsletter and possible suggestion of advertising using Flip Chart in N, R and Year 1 confirming that we are collecting "Nearly New" Uniform 1st week of school year. 16/09/14 Agreed that only collecting Deanery Emblem school wear, to be requested in next PTFA Newsletter will sell at Christmas Fayre | Rebecca Riddell | Completed | 2014-09-01
AP96 | 2014-02-11 | PTFA Social Media | Agreed that more information needed and suggestion that we could do a formal presentation to Mrs Yates. Committee to investigate further. 11/03/14 Action transferred to Kate Davazadeh to speak to Shelley Corbett about her availability to meet the PTFA Committee. Sarah Perks confirmed that Walmley, Whitehouse Common, Holyfield's and Little Sutton schools all have Facebook pages. 13/04/14 NL, RR, LG met up with Shelley to discuss FB. Very informative session. 30/04/14 Deanery Facebook Page launched. | Kate Davazadeh | Completed | 2014-04-30
AP97 | 2014-02-11 | DBS Checks - List of members and status of DBS checks | Lisa to establish current status of members and provide Jill with a list. Feb-14 Lisa has confirmed 9 members, 3 hold DBS with Deanery as their Employer, 6 to apply. Mar-14 Lisa to speak to Shirley (Bursar) to get forms out to individuals concerned. 14/04/14 email from Shirley Williams confirming that PTFA committee members do not meet the DBS criteria for volunteers in school and as such no action required. I have contacted PTA.Org who advise that we were mistaken DBS checks not required unless volunteers spend 2 nights per week in school or school stipulate. | Lisa Greenway | Completed | 2014-03-01
AP98 | 2014-02-11 | DBS Validity | As school will be the employer; Mrs Yates needs to confirm how long the DBS check is valid for. Action Jill. 11/03 Action transferred to Lisa, Lisa to speak to Shirley (Bursar) for validity. 13/03 Email from Shirley "I have had several emails from, and conversations with, advisors from our personnel company and the advice I have been given is that you do not need, and indeed it would be illegal, to do DBS checks for your members as you are not regular volunteers, you are in on an ad hoc basis. When in school you would need to be supervised by someone with a check – i.e.. If you need to go around school where there are pupils you would need to be accompanied. However, the onus is also on the teaching staff (and lunchtime supervisors) to ensure their students are not left unsupervised too. Hope this clarifies the situation" | Lisa Greenway | Closed | 2014-05-01
AP99 | 2014-03-11 | Quiz Night - additional Information on all Event Documents | Review of Quiz Night - request to provide additional information on flyer and ticket application. Mention raffle and Irish Bingo played on the night, contribution from raffle made to nominated charity | Rebecca Riddell | Completed | 2014-04-08
AP100 | 2014-03-11 | Quiz Night - Event Information | Review of Quiz Night - suggestion that Ticket returns need to go out to Team Captains earlier, particularly that new parents thought they had missed the deadline or maximum number exceeded. On-hold as reminder for next Autumn Quiz Nov-14 Reminded Maria that new parents need captain tickets returned to them ASAP. | Maria Hewett | Completed | 2014-10-08
AP101 | 2014-03-11 | Ready Steady Cook - A3 Flyers for School Doors | Lisa to print A3 colour Flyers x 10 and hand into School Office | Lisa Greenway | Completed | 2014-03-01
AP102 | 2014-03-11 | Ready Steady Cook - Collection of Money & allocation of tickets | Kate offered to complete this activity, Flyers out Thursday 13/3, last day for applications Wed 26th March | Kate Davazadeh | Completed | 2014-03-01
AP103 | 2014-03-11 | Ready Steady Cook - Alcoholic Refreshments | Natalie to try and get a deal on returning any un-used Wine (and Pimms - Summer Fayre). | Natalie Lockrey | Completed | 2014-03-01
AP104 | 2014-03-11 | Ready Steady Cook - Risk Assessment | Lisa to contact PTFA-Org and download relevant Document and Sub Committee to complete 14/03/14 Documents downloaded but not forwarded. Risk Assessment not completed for this event, but documents now available for future use. | Lisa Greenway | Completed | 2014-04-30
AP105 | 2014-03-11 | Summer Ball - Sub Committee | Natalie to speak to Rachael and agree what type of help she needs and when she needs activities to be completed. Once this is understood, need to enlist support. Suggestion - Flip Chart outside KS1 Classrooms, Spokesperson to speak after KS1 Best Work Assembly to encourage parents to help. 08/05 Natalie and Co supporting Rachael and Kira via Facebook etc. | Natalie Lockrey | Closed | 2014-05-01
AP106 | 2014-03-11 | Summer Fayre - Guests | Sarah to contact Mark Hayes - motorcycle paramedic, and see if he's available to attend 07/05/14 AP transferred to SF committee. Mark did not respond. | Sarah Perks | Completed | 2014-05-01
AP107 | 2014-03-11 | Summer Fayre - Football Tournament | SF Committee to agree and discuss the impact of the Football tournament on generating revenue a) should it be cancelled completely this year, or b) time reduced to enable "footballers" time on the All Inclusive Rides? AP Transferred to SF committee | Lisa Greenway | Completed | 2014-05-01
AP108 | 2014-03-11 | Summer Fayre - Promotional Material | As we are introducing the All Inclusive Ticket and more stalls this year, suggestion that this needs to be heavily publicised so Parents know in advance more activities to spend money on. May'14 - Included in May newsletter | Summer Fayre Committee | Completed | 2014-05-04
AP109 | 2014-03-11 | Hill West Fun Run | Hill West Primary School who are extending their 10k and 4k Fun Run to other schools. To be discussed at the next meeting. Bex to include in agenda. 08/04/14 included in April's agenda but not discussed, carried forward to next meeting. 08/05/14 Agreed that if we were going to get involved in Fun Run we would prefer to Host the event. | Rebecca Riddell | Closed | 2014-05-01
AP110 | 2014-04-08 | 2nd Quiz date to move from March to May | Maria Hewitt (Quiz Organiser) would like to move the 2nd Quiz from March to May. Officers to suggest a date for next May, agreed in principle. Requested that when considering the date committee takes into account the May B/H and Whitsun. 08/05/14 Revised date suggested in Year Planner | Officers | Completed | 2014-05-01
AP111 | 2014-04-08 | Disco - Reminders regarding parking and child protection issues | Reminders to be included on next terms Disco Ticket. 1) Parents not to park in front of emergency exist in staff car park. 2) Children and Parents are requested not to take pictures/video’s with phones – child protection issues. 10/06/14 Dave agreed that this information would be included in a one-off communication article to all Parents at the start of new school year. Advised that he would also be speaking to School Site Manager ref coning off emergency exit, making it clear to parents that they should not park in this area. 10/02/15 Lisa to send out reminders to Disco Sub Committee and ask if this AP has been addressed. 14/04/15 Reviewed and AP closed | Disco Committee | Completed | 2015-04-14
AP112 | 2014-04-08 | Sibling Link on printed material | The Easter Disco ticket applications appeared to go out to all year groups and the Sibling Link not used. 01/07/14 Mrs Cullen has taken away reminder to school office that Sibling Link not used 16/09/14 Mrs Cullen will obtain this year's sibling link numbers 03/10/14 Numbers received from Mrs Cullen n - 52 4 gaps of 13 rb - 30, rp - 29 1a - 24, 1s -26 2f - 24, 2g- 17 3d - 16, 3w - 22 4s - 15, 4w - 16 5s - 13, 5w - 11 6c - 14, 6m - 14 total 323 | Kirsty Cullen | Completed | 2014-10-08
AP113 | 2014-04-08 | Disco - Late Ticket Policy | Disco committee to agree Late Ticket Policy and provide guidance to Officers so that all parents are treated fairly and consistently. 10/06/14 Disco committee have agreed that all Late Ticket Requests should be referred to Disco Committee, contact details to be forwarded to Dave Archers Phone / email address. Last Day for tickets to be Tuesday before event of Friday. | Disco Committee | Completed | 2014-06-01
AP114 | 2014-04-08 | Disco - Risk Assessment Template | Disco Committee to work with Officers to create Risk Assessment for all future Disco’s 01/07 Summer Fayre committee producing a draft for review by School, once content agreed, generic risks to be forwarded to Disco committee, and specific risks associated with this event to be added. 08/10/14 Risk Assessment produced, question regarding adding signature. To be discussed at Dec meeting 14/01/15 Kirsty advised that school would not sign our documentation however they would ultimately be responsible for any PTFA event held on school grounds. All future RA to be sent into school via email address FAO Andy Clarke (who is schools Health & Safety representative). Agreed sub committee's should nominate individual to sign document, responsible for creation, updating and monitoring. | Disco Committee & Officers | Completed | 2015-01-01
AP115 | 2014-04-08 | Disco - Data Protection guidelines | Disco Committee to work with Officers to agree Data Protection guidelines for storing personal information. 10/06/14 Discussion around requirements, Dave agreed to include in Comms to All parents. 08/10/14 Lisa to provide a copy of the Girl Guiding Data Protection statement which may be useful to Disco committee. 10/02/15 Lisa to send out reminders to Disco Sub Committee and ask if this AP has been addressed. 12/05/15 Dave Rooney to obtain a copy of the statement. May-15 Confirmation received that Data Protection Information recorded on Disco Ticket Request and Risk Assessment | Disco Committee & Officers | Completed | 2015-05-12
AP116 | 2014-04-08 | Disco - Ratio's Parent to Child for KS1 / KS2 | Disco Committee to agree minimum ratio’s (Parent / Child) for both KS1 & KS2. (suggest that School Office should be consulted as should know numbers). 01/07 Mrs Cullen confirmed ratio's - R/N 1 ad : 5 ch, Year 1&2 1 ad : 8 ch, KS2 1 ad : 10 ch. These ratio's to be used for manning the Disco. | Disco Committee | Completed | 2014-07-01
AP117 | 2014-04-08 | Date of Yr. 6 Leavers Party | Confirmation of Yr6 Leavers Party date required so that DJ can be booked for event. Dave School Office. 10/06/14 Dave confirmed DJ booked. | Dave Archer | Completed | 2014-04-01
AP118 | 2014-04-08 | Summer Ball - request for volunteers | Bex to include request for volunteers to help dress the room on Saturday lunchtime and a gang to help clear the room on Sunday morning. May newsletter included request for help. | Rebecca Riddell | Completed | 2014-05-01
AP119 | 2014-05-08 | Lottery Licence | Lisa to confirm that all necessary steps completed so SF tickets can be promoted. Reviewed Good to go. | Lisa Greenway | Completed | 2014-05-01
AP120 | 2014-05-08 | Facebook - rules of engagement | PTA-Org policy template downloaded, some minor amendments to add in. AP120 Bex to update and show as link on FB page | Lisa Greenway | Completed | 2014-05-01
AP121 | 2014-05-08 | Completion of Profit & Loss Spreadsheet per Event | Committee members present agreed that Treasurer responsible for reminding Sub Committee's that spreadsheet should be completed within 2 weeks of event date and all funds should be banked within 7 days. Event Template to be updated to reflect these agreements. | Lisa Greenway | Completed | 2014-05-01
AP122 | 2014-05-07 | New Events and Organisers to be discussed at next Mtg. | Fun Run, RSC, Ladies Night, Table Top Sale All added to Agenda for June Meeting | Bex Riddell | Completed | 2014-05-01
AP123 | 2014-05-07 | Application for New Bank A/C with CAF | PTA.Org advertise using CAF bank for PTFA funds, ability to pay-on-line, debit card etc. 10/06 Michelle confirmed application made, not heard anything yet. 01/07 Paper application received. Agreed that we should proceed with 3 people nominated to have debit cards, Natalie, Michelle and Paul. Request to proceed with paperwork so that bank a/c up and running for start of new school year. Existing Bank a/c to remain open in order to deposit cheques. Oct'14 Michelle confirmed that following a conversation with existing Bank (Lloyds) it is possible to request Debit Cards and use on-line banking. Michelle to set up Jan'15 Michelle distributed debit cards and pin numbers to Bex, Nat and Lisa | Michelle Dolphin | Completed | 2015-01-01
AP124 | 2014-06-10 | Voucher Scheme - Summer Fayre | Suggestion to introduce voucher scheme for payment of entrance fee and stalls. Removes the need to count money and arrange floats etc. Bex to add to SF Event Template for next year. | Bex Riddell | Completed | 2014-07-01
AP125 | 2014-06-10 | Thank-You gift for John Morris | Dave Archer to purchase a suitable gift up to £20.00 to give to John for recognition of Disco work. 01/07 Reminder to Paul that this is still o/s 09/12/14 following meeting today, the committee agreed that volunteers/organisers should be recognised by receiving a personalised thank-you letter from the PTFA. the purchase of a gift is no longer appropriate. | Dave Archer | Cancelled | 2015-01-01
AP126 | 2014-06-10 | Just Text Giving | Rachael offered to investigate how PTFA would set this up, when and how it could be used. 01/07 Rachael advised that having set up Just giving webpage, Just text allows sponsors to pay via text. No cost to set up or when sending text. Agreed limited use, however useful for Fun Run. Agreed Rachael to pursue. 16/09/14 Rachael confirmed that too expensive for limited use by PTFA | Rachael Smith | Completed | 2014-09-01
AP127 | 2014-06-10 | Fun Run Organisers | Lisa to contact Deborah Wilkinson and Claire to confirm if they are willing to organise the Fun Run (Sunday 12th October) 01/07 Deborah has agreed to support, Natalie, Bex and Mrs Cullen also on board. Mrs Yates not available on the 12th October, proposed date change 5th. Agreed | Lisa Greenway | Completed | 2014-07-01
AP128 | 2014-06-10 | Ready Steady Cook Organiser | Lisa Middleton has in principle agreed to run another event, but won't be in a position to confirm availability until Jan 2015 with work commitments. PTFA committee will support Lisa with all paperwork required. (Friday 6th February). 14/01/15 Lisa confirmed that she is available to deliver RSC | Committee Members | Completed | 2015-01-01
AP129 | 2014-06-10 | Pamper Night Organiser | Rachael to speak Kira and ask if should would be willing to Organise Pamper Night (Friday 13th March). 08/10/14 Rachael advised that Kira is unable to Organise event. Agreed to put out a request for help in the next PTFA Newsletter. 14/01/14 No-one has come forward to coordinate event so agreed unable to proceed. Jan'15 - Final request for help before event cancelled. | Rachael Smith | Completed | 2015-01-14
AP130 | 2014-06-10 | Table Top Sale format | Bex to speak to Helen Williams to ask her to get a copy of the format used by Fairfax so that Committee could consider running the same event. 16/09/14 Have copy of format - Helen happy to work with Bex to plan. Confirmation that the Saturday has been agreed with School. Jan'15 Bex confirmed Helen Williams and Claire Arrowsmith on board as sub-committee | Bex Riddell | Completed | 2015-01-01
AP131 | 2014-06-10 | Nursery Welcome Party Organiser | Natalie to speak to Kate Davazadeh to ask if she would be willing to Organise event. 01/07 Kate has agreed to take on event. Lisa to send Kate Nursery Event Template. | Natalie Lockrey | Completed | 2014-09-01
AP132 | 2014-07-01 | Access to Craft Room for SF volunteers 4th July | Request to School to have access to Craft Room during Friday to prepare stalls. Kirsty Cullen Access agreed | Kirsty Cullen | Completed | 2014-09-01
AP133 | 2014-07-01 | Public Liability Disclaimer - Lichfield Inflatables | SF committee to obtain copy of PL disclaimer from Lichfield Inflatables Copy obtained | SF committee | Completed | 2014-09-01
AP134 | 2014-07-01 | Raffle Prize - Claire Baker Photography | Bex to email Claire Baker Photography and confirm that we would like to take them up for the offer of Photo shoots but use at alternative event. 18/07/14 Email sent. Reply received saying offer fine for next school year and requesting contact to discuss further. They are able to provide more than 10 vouchers if we need. | Bex Riddell | Completed | 2014-09-01
AP135 | 2014-07-01 | Funding Request - Pantomime 2014 | Bex to include Pantomime as Agenda item for PTFA meeting 16/09/14 Mrs Cullen to complete PTFA funding Request template so that we have all the details available to make a decision. | Bex Riddell | Completed | 2014-07-01
AP136 | 2014-07-01 | First Aid Kit - restocking of items | Officers to investigate the cheapest way of re-stocking First Aid Kit 16/09/14 Suggestion that we should ditch the 3 individual boxes in preference for one big bag. Kirsty mentioned Sportsco Football use bags rather than boxes. 19/09/14 Lisa purchased First Aid Bag in the sale £15.00, existing boxes emptied and contents checked off against St Johns FA List (sourced by Dave Archer). Dave's original concern of poor content not substantiated. Ice-packs main items that need to be purchased. Natalie has ordered 50 packs on-line. Waiting receipt. 25/09/14 Bex has emailed Deanery Office and asked if they have an existing FA contents list, and if it would be possible to re-order stock on the back of school orders. Waiting for response. Office have advised that PTFA can source first aid contents as cheaply from other outlets i.e. pound land. 10/02/15 Lisa to send Bex St Johns FA List, to be photocopied and held in the FA bag. Sub Committee's responsible for checking content before their next event. 16/03/15 Lisa has completed contents list, Natalie has returned First Aid Register. | Committee Members | Completed | 2015-03-01
AP137 | 2014-07-01 | Thank-You to Sub Committee Organisers | Bex to include Thank-You'd as Agenda item for PTFA meeting 16/09/14, Who, When and What value? | Bex Riddell | Completed | 2014-07-01
AP138 | 2014-07-01 | Site Managers Payments | Bex to include Site Managers Payments as Agenda item for PTFA meeting 16/09/14, When and How Much? | Bex Riddell | Completed | 2014-07-01
AP139 | 2014-09-16 | Flowers for Mrs Yates | Natalie to order so that we can present at AGM. | Natalie Lockrey | Completed | 2014-10-01
AP140 | 2014-09-16 | AGM meeting 2015 | Suggestion that in order to meet critical number of persons present at meeting should incorporate into another popular event i.e. Quiz night. 17/05/15 those present at the meeting discussed whether we should incorporate within another event. Consensus that this year we should keep separate. | Committee Members | Closed | 2015-06-01
AP141 | 2014-09-16 | Purchase of additional equipment Gazebo's & Folding Tables | Discussion around current quantities and styles of gazebo’s and tables owned by PTFA and how we do supplement with Parents property. As the shed has now been “made good” we now have somewhere suitable to store such equipment. Agreed not right to keep using “parents” property but unable to reach agreement on quantity to purchase and prices. To be carried forward to next meeting. 08/10/14 Suggested that we should ask school if they would be willing to contribute to the purchase of additional tables, which school would be able to use. Rachael advised that she may be able to borrow some collapsible tables from work. Dec'14 Consensus reached to purchase 6 x folding Tables @ £40 each, 2 x Gazebo maximum of £500. 10/02/15 Although we have funds, we agreed that we would postpone purchasing these items until we have sufficient space in our shed. Feb-15 Folding tables (x6) purchased from Costco. Gazebo's outstanding. 14/04/14 Update from Deborah 1 x Large and 4 x Small Gazebo ordered cost £629.26 | Committee Members | Completed | 2015-04-14
AP142 | 2014-10-08 | Setting up Gift Aid | Lisa and Michelle to complete the necessary paperwork in order to claim back the Gift Aid donations given by parents for the Fun Run event. Jan-15 Lisa has contacted HMRC, who have confirmed that Friends of Deanery have already registered and the previous unique reference number is still valid. Before we can enter Gift Aid details we need to notify them of change of personnel via nominated form. Information passed to Michelle. Jan-15 Michelle has confirmed unable to open on-line document, paper copies requested from HMRC Feb-15 Lisa has completed on-line element of change form, Michelle, Bex and Lisa have signed relevant paperwork, waiting for Karen Taylor (previous Treasurer) to sign document relinquishing responsibility and endorsing new committee. Mar-15 - Michelle has sent off the relevant paperwork waiting update from HMRC. May-15 - paperwork received stating that HMRC cannot proceed until a previous person known to HMRC relinquishes their responsibility. AP transferred to Helen, Karen Taylor works at Fairfax so Helen offered to get document signed. Jun-15 - Helen will resolve by 19/06/15 Jul-15 - Helen not at the meeting, Bex to text to see what the current position is. Sept-15 - Helen has been unable to move this forward, several failed attempts to download document and a number of system crashes on school equipment. Michelle to locate the correct form and confirm details to Helen. Oct-15 Bex to locate for CHV1 print a copy and forward to Helen. Feb-16 Bex confirmed still in hand Mar-16 Bex has been able to print off a blank template and has handed to Helen Williams. Helen has attempted to get hold of Karen Taylor but as yet no signature. Jul'16 Form with Helen waiting to be signed by Karen Taylor. Sep'16 Bex has got Karen Taylor (previous Treasurer to agree on content) and sign document allowing us to register to change details. Jun'17 Bex confirmed that HMRC have acknowledged her as chair. Michelle to move this forward | Michelle Dolphin | On-going | 2017-01-17
AP143 | 2014-10-08 | Engaging with Parents and encouraging participation (A) Facebook | Long discussion ref how we engage with parents. Agreed that it may be useful to have a banner promoting find us on Facebook. Jan-15 Bex has created a banner template, content reviewed. Agreed to add "Parents" get involved, to ensure we don't encourage Deanery children to have a Facebook a/c. Bex to make amendment and forward to Michelle for Andy to produce. Feb-15 Completed, banners positioned on both school gates | Michelle Dolphin | Completed | 2015-02-10
AP144 | 2014-10-08 | Engaging with Parents and encouraging participation (B) Twitter | Bex to set up a twitter account | Bex Riddell | Completed | 2014-10-01
AP145 | 2014-10-08 | Engaging with Parents and encouraging participation (C) Review of Newsletter format and content, Contact List, Setting Up Parent Helper List | Committee to look again at all documentation to see if better way of promoting PTFA activity and requesting support. Jan-15 Format of Newsletter changed, with Sub titles introduced to help parents focus on subject areas that are of interest to them. Jan PTFA newsletter has gone out on the back of the school newsletter. Committee believe that this is a very positive step forward and hope that more parents will be encouraged to read our newsletter. Mrs Cullen confirmed that this will continue in the future. Agreed that this negates the need to create a contact list for parent helpers. | Committee Members | Completed | 2015-02-01
AP146 | 2014-10-08 | Engaging with Parents and encouraging participation (D) Noticeboards | Committee to look again at utilising existing school Noticeboard in KS1 playground and purchasing 2 new ones for both playground entrances. Feb-15 Penn's and Walmley school are both using external noticeboards to promote PTFA activities. Despite only 7 families requesting paper copies of the school newsletter, we agreed that we should consider installing 2 noticeboards on the front and back gates. Mrs Cullen confirmed that Sarah Perks obtained a price from the same provider used by the Children's Centre approx. £1100. Mrs Cullen will approach a parent at school who was involved in the school signage to see if they would be able to help source items. Mar-15 Miss Ainsley has not received an update from Mrs Cullen. Apr-15 Lisa has spoken to Walmley School who have installed 2 x Noticeboards, both were purchased from the same supplier as The Children's Centre - Jackie Darcy's contact. AP transferred Michelle to speak to Jackie Darcy and obtain relevant information. May-15 Michelle confirmed that original supplier of noticeboards has gone out of business. She has been advised that a parent within school has a business in this line of work. Michelle to explore. Jun-15 Michelle confirmed that she has identified a possible supplier, size fits 8 x A4 posters, £100 white, £180.00 silver. this does not include the Branding element - i.e. Deanery. Michelle to establish if VAT on top, P&P. Rachael to ask Jackie Darcy if we can utilise the Children's Centre Noticeboard. If not possible consensus by all those present that Michelle should place an order for 1 board. Jul-15 Andy Dolphin has done a lot of research, £500 includes everything. Michelle to place order. Jul-15 Michelle advises that Mrs Luckett will need to review proposal before order can be placed. Sep-15 Michelle to send details to Miss Ainsley for onward review by Mrs Luckett. Oct-15 No update from school as yet. Feb-16 Lisa to speak to Mrs Luckett to move this forward. Mar-16 No further update Jul'16 Awaiting approval for size 8 x A4 and placement next to Children’s Centre noticeboard to be approved. Sep'16 Michelle has received quote £491.47, proceeding to order placement. | Michelle Dolphin | Completed | 2016-09-13
AP147 | 2014-10-08 | Use of School Cash Office for PTFA events? | Kirsty to ask Mrs Luckett to consider PTFA request. 14/01/15 School have advised that this isn't really an option, as the school pays a transaction charge for each payment made it would not be financially viable. The Bursar can also se difficulties with banking. at this point school office have said no. | Kirsty Cullen | Completed | 2014-01-01
AP148 | 2014-10-08 | Job Descriptions and Constitutional Information posted on Webpage. | Lisa to arrange for information to be made available. Jan-15 Documents reviewed and minor tweaks made to reflect current responsibilities. Lisa to forward to school for uploading to website. Feb-15 Uploaded to Website. | Lisa Greenway | Completed | 2015-02-01
AP149 | 2014-11-11 | Update of Charities Commission Website | Lisa to obtain personal details from the New Ordinary Members to enable the Charity Commission Website to be updated with the Trustee’s information. | Lisa Greenway | Completed | 2014-12-01
AP 150 | 2014-12-09 | Risk Assessment - Ownership & Responsibility? | 09/12/14 Paul Lord (Disco committee) raised question regarding who signs off the individual risk assessment. 14/01/15 Kirsty confirmed that school wouldn’t sign the risk Assessment document however they would accept ultimate responsibility for an event carried out on school premises. Agreed that a nominated individual from each sub committee should create, hold, update and sign document. School have requested that all RA should be sent via school email address FAO Andy Clarke, as the site manager is the schools Health & Safety rep. | Kirsty Cullen | Completed | 2015-01-01
AP151 | 2014-12-09 | Temporary Event Notices - Potential Changes to criteria for use. | The PTA.Org have recently published an article on website advising that the Government are currently reviewing the Licensing Criteria and the impact of the red tape on small business’ and charities. The suggestion is that we may only need to apply for a licence if we are selling alcohol. Decision to be reached by end of March 2015. 25/02 Lisa contacted both PTA.org and BCC Licensing Dept., neither party able to provide update at this present time. 22/04/15 Update to Licensing Laws came into force on 06/04/15 relates to entertainment licensing. TEN no longer required for a FILM Night as long as no charge for entry, as long as event takes place on school premises and all other film related licenses/restrictions apply. TEN no longer required at an event on school premises where there is music, either live or recorded, such as a school disco as long as alcohol is not supplied. TEN no longer required for circuses. Following points remain unchanged. TEN required at any event where alcohol is supplied. Any event of over 500 people will need a Premises licence. Only 5 TEN cab be obtained per person, per year. | Committee Members | Completed | 2015-04-14
AP152 | 2014-12-09 | Replacement Shed | 09/12/14 Kirsty to ask management if we can erect larger shed, in the current location. 14/01/15 Site manager has agreed that we can erect a slightly bigger shed but has stipulated that it must fit in the current space and on the existing hard standing. 09/02/15 Site manager has confirmed current shed 8x10', hard-standing same size, limitations for installing bigger shed. | Kirsty Cullen | Completed | 2015-01-01
AP153 | 2015-01-14 | Location of First Aid Bag and additional contents | Committee to ensure First Aid bag and contents available in PTFA cupboard. Bex to ensure in correct location. | Committee | Completed | 2015-02-01
AP154 | 2015-01-14 | Suggestions for new ideas at School Disco | Kirsty to put suggestions forward to the School Council of how or what children would like to see different / participate in at the school disco. Jan-15 Request put forward to Mrs Sharp waiting for feedback. Mar-15 Rotary volunteers (Year 6) confirmed that Cameron Sohal (School Council Representative) has consulted them and recorded their suggestions. Formal Feedback has not yet been received from Mrs Sharp. Apr-15 Mrs Sharp has provided a list of changes requested by the KS2 children. 65 children took part in the survey. 28 Yes to Louder Music 46 Yes to More Boys related toys and stalls 60 Yes to separate disco for Yr. 5&6. 65 Yes to using U-Tube. 60 Yes to better food. 63 Yes to cheaper food. 53 Yes to Karaoke competition. 59 Yes to Street Dancer. | Kirsty Cullen | Completed | 2015-04-14
AP155 | 2015-01-14 | Specific Target or item to be funded for 2015 | Kirsty to speak to the teachers, management and School council for specific projects or items that we can purchase or contribute to. Jan-15 Request put forward to Mrs Sharp waiting for feedback. Apr-15 Miss Ainsley has asked teachers directly but at the point of raising question no requests made. May-15 Miss Ainsley unwell and not present at this meeting. No update available. Jun-15 No new requests received this school year. Closed | Miss Ainsley | Closed | 2015-06-17
AP156 | 2015-02-10 | Easter Egg for every child in school | Miss Ainsley to confirm total number of children and exceptions 468 - agreed to purchase 480. | Miss Ainsley | Completed | 2015-02-01
AP157 | 2015-02-10 | Purchase of individual Easter Eggs and 3 x competition winners | Dave and Deborah to source and arrange storage with school. Individual eggs (max 0.75p per egg) to be in school before 27th March. Also to source 3 “spectacular” eggs for competition winners (max budget £25.00) to be in school before 12th March so that could be available for promotion in assemblies. Feb-15 Given to Office Staff. Purchase price £20.00 | Dave Rooney Deborah Wilkinson | Completed | 2015-02-01
AP158 | 2015-02-10 | Local Estate Agents expressed interest in sponsoring school event | Kirsty to identify name and contact of local Estate Agents in Walmley who wish to actively sponsor a school event and forward onto Rachael Smith (Summer Ball organiser). Mar-15. Miss Ainsley was unable to provide an update. Apr-15 Mrs Cullen is unable to locate the details relating to this offer. Rachael will need to make personal contact with business's operating in Walmley. | Kirsty Cullen | Cancelled | 2015-04-01
AP159 | 2015-02-10 | New PTFA Shed | Kirsty to approach nominated supplier to see if they would be prepared to do a deal on a plastic shed (minimum size 8 x10’) for use by PTFA. Mar-15. Miss Ainsley was unable to provide an update. Apr-15. Agreed that the PTFA should take back the responsibility for moving this AP forward. May-15 Committee has agreed on a 10 x 8 ft. metal shed. Natalie has worked hard to secure at the best price £294.99 but then let down by supplier - no stock. Provisional date agreed of 6th June to dismantle and clear old shed and erect new. Working Party cancelled and new date agreed of 11th July for dismantling of shed. Jul-15 Issues raised with school office and escalated to Mrs Luckett, regarding school property next to shed that needs to be moved in order to get full access. Jul-15 None of the work that was agreed to be completed by the Site Manager was actually removed. Letter of disappointment to be sent to Mrs Luckett. 25/09/15 Natalie and Lisa attended meeting with Mrs Luckett above was discussed. Action Point left open as 2nd shed for storing PTFA tables and shelving required. 07/10/15 All present at the meeting agreed that we need to purchase a 2nd Shed ASAP (up to the value of £250) plus shelving. 12/01/16 Natalie has identified Ketler Shed's that may be suitable to house the fold-away tables. Lisa confirmed each storage box would only take 5 tables each. Agreed to revert back to original spec of metal shed, double doors. 10 x 4 ft. 03/02/16 New shed ordered, delivery requested for w/c 22nd Feb, volunteer working party confirmed "shed" building activity set for Saturday 27th Feb. Feb'16. School have requested to "down tools" and will not allow us to erect shed without first writing to neighbours to give advance warning of any noise that might be generated by this activity. Mar'16 Email from school that Andy Clarke has offered to erect the shed, endeavour to complete before Summer Term. PTFA have accepted offer, but also provided alternative dates for working party should Andy not fulfil obligation. Waiting to see if work completed within timeline. May'16 Shed installed. | Committee Members | Completed | 2016-05-17
AP160 | 2015-03-11 | DJ Documentation | Dave to obtain copies of PAT test and DBS certification for DJ's 14/04/15 Provided and information reviewed. | Dave Archer | Completed | 2015-04-01
AP161 | 2015-03-11 | Proposed new date for Summer Fayre | Miss Ainsley to urgently check if the NEW proposed date (26th June) would be agreeable with school. Current date (3/7/15) clashes with TKD practice session for grading the following day. Expect this to have a negative impact on both attendance and volunteers at the fayre. 14/04/15 School are unable to accommodate a change of date at this stage in the school year. | Miss Ainsley | Completed | 2015-04-01
AP162 | 2015-03-11 | Request for school to support coach transport Year 6 Leavers Meal | The committee have agreed to provide FOC return coach from the school coach park to Lea Marston Hotel. Lisa to ask school to endorse offering by incorporating it into the school communication to parents. Mar-15. Mrs Luckett would like this transition from Parent Lead to PTFA lead transport to be completed independently. | Lisa Greenway | Completed | 2015-03-01
AP163 | 2015-04-14 | Thank-You Letter Miss Braniff | Apr-15 Natalie to send thank-you letter to Miss Braniff for her generous donation of toy Bunny. May-15 Composed and handed to Miss Braniff | Natalie Lockrey | Completed | 2015-05-12
AP164 | 2015-04-14 | Stakeholder Questionnaire | 01/04/2015 Suggestion that we could ask Mrs Luckett if she would be happy for us to create a questionnaire for completion in school by each class and their teacher as to where or what projects PTFA profit could be used for. Parents to have access to the same document via our website. May-15 Miss Ainsley unwell and did not attend this meeting - no update provided. Jun-15 No update Jul-15 Mrs Luckett has asked PTFA to come up with a draft, content to be reviewed and agreed. Oct-15 Bex confirmed that Helen W had come up with an initial draft, Lisa to locate and review content. Feb-16 Lisa advised that she could not locate the original draft, new one to be created and sent in to Mrs Luckett for review and agreement. Mar-16 Lisa requested the help of Helen W to create a new draft for Lisa to work on. Jul-16 AP withdrawn, insufficient activity to take it forward, to be picked up again if required | Lisa Greenway & Helen Williams | Withdrawn | 2016-07-04
AP165 | 2015-05-12 | Funding Document | May-15 Bex to provide copy to Miss Ainsley for forwarding on to staff, teachers and governors. Lisa to get copy uploaded to our area of website. | Bex Riddell & Lisa Greenway | Completed | 2015-05-01
AP166 | 2015-05-12 | Spring Disco - Breakdown of Finance Report Outstanding | May-15 Dave Rooney to escalate to Dave Archer - overdue. | Dave Rooney / Dave Archer | Completed | 2015-06-01
AP167 | 2015-05-12 | Quiz Night Documentation | May-15 Maria asked that promotional material be updated to extend invite to parents, friends & neighbours. | Bex Riddell | Completed | 2015-05-01
AP168 | 2015-05-12 | Summer Ball - request to donate some of the profits to external charity specialising in Family Bereavement Services | May-15 Racheal requested to first ask school if the Deanery would be interested in training a 2nd councillor. Jun-15 Rachael confirmed that school advised that they were trained by Edwards Trust, Deanery Families are still using the services. Agreed that this would be nominated external charity. Discussion whether profit from photo booth could be donated to Edwards Trust. Noted that because we have to first cover £270 hire cost that this might not be as advantageous to the trust as other gaming options on the evening. | Rachael Smith | Completed | 2015-06-01
AP169 | 2015-05-12 | 2015-2016 PTFA Events Calendar | May-15 Lisa to provisionally come up with a schedule and send to Event Organisers to review and confirm dates | Lisa Greenway | Completed | 2015-06-01
AP170 | 2015-05-12 | Charity Commission Records | May-15 Lisa to amend our Trustee Details - remove Mrs Cullen and replace with Miss Ainsley | Lisa Greenway | Completed | 2015-05-01
AP171 | 2015-05-12 | Yr. 6 Leavers Meal - PTFA funded Coach | 01/05/2015 Natalie to review initial document and modify to include Emergency Contact details and last chance to opt out. | Natalie Lockrey | Completed | 2015-05-01
AP172 | 2015-06-17 | Quiz Money not yet Banked | Natalie to text Maria as a gentle reminder. Jul-15 Money banked £218 profit made. | Natalie Lockrey | Completed | 2015-07-08
AP173 | 2015-06-17 | Yr.6 Leavers Meal - Docking Station, Music, Decorations for Coach + Deanery Leavers Photo Sheet + Risk assessment | Jun-15 Natalie to provide docking station, Deborah to purchase decorations, balloons and create IPOD list. Miss Ainsley to ask Yr6 teachers if they would be willing to decorate a white bed sheet, with Deanery Leavers for photo's. Jul-15 Yr6 too busy to create photo-shoot backdrop. Natalie will create. Jul-15 Risk Assessment completed and signed off by school office. Sep-15 59 children signed up, fantastic success. Lots of parents expressed gratitude both on the evening and in the playground. Letter of thanks from Denise (mum of Claire). | Natalie Lockrey Deborah Wilkinson Miss Ainsley Lisa Greenway & Bex Riddell | Completed | 2015-07-08
AP174 | 2015-06-17 | Forever Living – Wellbeing Evening | Lisa to propose a date in Autumn Term. 08/07 Friday 13th November proposed in the PTFA calendar. | Lisa Greenway | Completed | 2015-07-08
AP175 | 2015-06-17 | Teddy Bear Picnic Events 2015 | Offer for PTFA to attend events declined, Natalie to speak to Sue in the Office Jul-15 Natalie has declined the offer to attend the meeting. | Natalie Lockrey | Completed | 2015-07-08
AP176 | 2015-06-17 | Text Reminders | Formal request into school to ask how much it would cost PTFA to send a text to sibling link register. 8-Jul Miss Ainsley has confirmed no need to pay, cleared with Mrs Luckett. | Miss Ainsley | Completed | 2015-07-08
AP177 | 2015-06-17 | Soil Survey of School Grounds | Lisa to locate the soil survey completed several years ago on the school grounds. For review by Mrs Luckett, with view to school considering draining the fields in order to get more use out of them. 08-Jul Maria thinks she may have a copy of the document. 14-Jul Maria confirmed that she no longer has the document. 06-Aug & 02-Sep text sent to Mark Bessy (Parent Governor on Buildings Committee) no response. 16-Sep AP transferred to Racheal. To take to full Governors meeting next week. 07-Oct Rachael not present at this meeting so no update 04-Nov-15 As school are looking at school grounds and possible "BIG funding opportunity". Assume school will get their own soil survey completed. | Rachel Smith | Closed | 2015-11-01
AP178 | 2015-07-08 | Summer Ball - proceeds of raffle | Rachael to confirm that £480 represents the profit from the raffle as previously agreed. Sep-15 Rachel confirmed yes. Michelle to raise cheque for Edwards Trust. | Rachael Smith | Completed | 2015-09-16
AP179 | 2015-07-08 | Nursery Welcome Party - Risk Assessment | Lisa and Bex to create risk assessment. | Lisa Greenway & Bex Riddell | Completed | 2015-09-01
AP180 | 2015-07-08 | Nursery Welcome Party - Speech | Miss Ainsley to ask Mrs Luckett if she is available to do a welcome speech at Nursery Party. Sep-15 Mrs Luckett has confirmed that she is available. | Miss Ainsley | Completed | 2015-09-01
AP181 | 2015-07-08 | Timeline per Event | Following the Summer Fayre review it was suggested that once PTFA Event dates agreed by school that committee review each event and create a timeline for documentation to be created, printed and distributed. Agreed that where a sub-committee exists the Lead Person should review and communicate back to Committee to build into overall schedule. | Lisa Greenway & Bex Riddell | Closed | 2015-12-09
AP182 | 2015-09-16 | Disco Income & Expenditure | Dave Rooney to chase Dave Archer for information. Michelle advised that she has sufficient information for the accounts and that the income and expenditure was a nice to have but not essential. | Dave Rooney | Withdrawn | 2015-09-16
AP183 | 2015-09-16 | Disco request to use SCO pay | Dave has reviewed the Ticketing process and believes that there could be a simpler solution, disco committee would like school to consider PTFA using SCO pay. Dave to email Miss Ainsley. 08/03/16 Dave confirmed that he has completed some initial assessments and would still like to pursue this as a possible option, will pick up after Easter. 04/07/16 There has been changes in office staff. Currently the answer to using Scopay is no, however they are happy to review this at a later date. Dave to explore other potentials such as paypal. | Dave Rooney | Closed | 2016-07-04
AP184 | 2015-09-16 | Date of Yr. 6 leavers Meal (July'16) | Dave has requested date so that he can book the DJ. Lisa to email Miss Ainsley. Nov-15 Date confirmed Oct-15 School do not currently have a confirmed date, will let PTFA know when they have organised event. | Lisa Greenway | Closed | 2015-11-01
AP185 | 2015-09-16 | Disco Changes | Dave and the committee to come up with some suggestions on how to improve the disco. Suggestions to be sent via S. Ainsley. 03/02/16 Agreed that this should be transferred internally to Disco Committee for review and action if required. | Dave Rooney | Closed | 2016-02-01
AP186 | 2015-09-16 | AGM - Change of Date | Natalie has personal commitment and cannot attend proposed date. New date suggested as Tues 3rd November. New date agreed by school | Lisa Greenway | Completed | 2015-10-01
AP187 | 2015-09-16 | Father Christmas Visit to school | PTFA would like school to confirm if Tuesday 1st December agreeable for Father Christmas visit. School confirmed ok. | Lisa Greenway | Completed | 2015-10-01
AP188 | 2015-09-16 | Friendship Bench | Natalie to send a picture of the friendship bench to Miss Ainsley to ask if school would like the PTFA to provide one. School have confirmed that happy to receive friendship bench. PTFA to decide whether to revamp existing or purchase new. Natalie to pursue with Beth (Parks Ranger). 08/03/16 Nat to speak to Beth. 17/05/16 School are installing a friendship bench in memory of Isobelle. Agreed that did not want to detract from it's meaning, | Natalie Lockrey | Closed | 2016-05-17
AP189 | 2015-11-04 | Appointment of an Independent Examiner | Michelle to ask Ruth Boon to take on this responsibility (she has previously completed this task and is familiar with the process. Toby Arrowsmith has completed review, and sent a number of questions regarding content to Michelle. | Michelle Dolphin | Completed | 2016-02-01
AP190 | 2015-11-04 | Charity Commission Records - to be updated | Lisa to obtain /check personal details from the Ordinary Members to enable the Charity Commission Website to be updated with the Trustee’s information. Lisa confirmed Sarah Perks and Mrs Cullen removed from the trustee list, only Jo Thuys to provide personal details. 08/03/16 Trustee information up-to-date | Jo Thuys | Completed | 2016-03-08
AP191 | 2015-11-04 | Ethos Committee Volunteer | Mrs Luckett to send through an overview of role that could be forwarded to PTFA members. Michelle Dolphin has volunteered. First meeting attended. | Michelle Dolphin | Completed | 2016-02-01
AP192 | 2015-12-09 | Nursery Christmas Event | Miss Ainsley to explore if Nursery they are doing anything in house for Christmas and do they want funding. Michelle advised that they didn't do anything for Christmas and Nursery staff aware of "Funding Request" form. | Miss Ainsley | Closed | 2016-02-01
AP193 | 2015-12-09 | Quiz Night External Charity Donation | Maria to confirm Quiz Night donation value. Consensus from those present at the meeting that 10% of profit to be donated to Pinky Purple Charity. Michelle to arrange payment. 08/03/16 Michelle confirmed £25 donation sent to Pinkie Purple. | Michelle Dolphin | Completed | 2016-03-08
AP194 | 2015-12-09 | New Quiz Night Organiser | Bex to put advert for new parent quiz organiser in PTFA Newsletter. 08/03/16. Bex confirmed information included. Natalie has suggested that Ness and Sam Isley may be interested. Nat spoke to Ness and "yes" willing to take it on. Natalie to speak to Maria and for a handover to take place during next Quiz Night. | Bex Riddell / Natalie Lockrey | Completed | 2016-03-08
AP195 | 2015-12-09 | Business Enterprise Team | Michelle to confirm with school number of children who made up winning Business Enterprise Team and purchase £5.00 Sutton Mall vouchers. Michelle confirmed numbers, Natalie purchased Mall Vouchers. | Michelle Dolphin | Completed | 2016-01-01
AP196 | 2015-12-09 | Christmas Fayre Craft Items | Lisa / Kira to make sure all Christmas Craft items left over from CF to be made available to sell at the Disco. | Lisa Greenway | Completed | 2016-01-01
AP197 | 2015-12-09 | Jolly Jungle Funding Request | Miss Ainsley to obtain more details regarding request for Jolly Jungle and complete PTFA funding Request Template for PTFA records. Template completed and consensus agreed, items purchased | Miss Ainsley | Completed | 2016-02-01
AP198 | 2015-12-09 | Dressing Up Clothes Funding Request | Miss Ainsley to obtain more details of the type and quantity of dressing up clothes and complete PTFA funding Request Template for PTFA records. 08/03/16 Miss Ainsley not present at the meeting - carried forward. 17/05/16 closed pending form | Miss Ainsley | Closed | 2016-03-08
AP199 | 2015-12-09 | Toy Service Date | Miss Ainsley to explore with Mrs Luckett if Toy Service could be moved to alternative week. Response "No". Discussion whether we can swap dates of Disco and Christmas Fayre and impact on Father Christmas visit. Agreed in principle that this could work. Committee to reflect these changes when dates for the following year submitted to school. | Miss Ainsley | Completed | 2016-02-01
AP200 | 2015-12-09 | Snowdome Voucher - Fun Run | Lisa to review with Deborah if Snowdome voucher still outstanding and purchase if necessary | Lisa Greenway | Completed | 2015-12-01
AP201 | 2016-01-12 | PTFA Debit Card for Disco committee | Michelle to arrange for PTFA debit card for Dave use for discos. 08/03/16 Michelle and Dave have agreed that he can "temporarily use" one of the existing cards rather than request an additional card. | Michelle Dolphin | Cancelled | 2016-03-08
AP202 | 2016-01-12 | Re-schedule date Film Night | Miss Ainsley to check whether film night can be rescheduled to either 21st, 22nd, 28th or 29th April. Miss Ainsley confirmed new date 22/04/16 | Miss Ainsley | Completed | 2016-02-01
AP203 | 2016-01-12 | Re-schedule date Ready Steady Cook | Miss Ainsley to check whether Ready, Steady, Cook can be rescheduled to either 26th February, 4th or 11th March. Miss Ainsley initially confirmed 11/03/16, and Lisa Middleton can make it, however Mr Clarke has now advised that he doesn't wish to do attend school 2 consecutive Fridays. Miss Ainsley to ask if 04/03/16 ok? Feb'16 Lisa spoke to Mrs Luckett ref channels of communication, Mrs Luckett requested that "scenario" be emailed into school office so that she can review and comment. due to work pressures Lisa unable to complete this. Missed opportunity to re-organise event, cancelled for this year. | Miss Ainsley | Cancelled | 2016-03-01
AP204 | 2016-01-12 | Timeline Mother's Day Hampers | Natalie and Bex to confirm timeline to Claire for Mothers’ Day Hampers. | Natalie & Bex | Completed | 2016-02-01
AP205 | 2016-01-12 | Easter Egg competition Handover Notes | Bex to email Jo Thuys with details as to what needs doing for Easter competition. | Bex Riddell | Completed | 2016-02-01
AP206 | 2016-01-12 | Prizes for Easter Egg Competition | Deborah to purchase a prize Easter egg for Nursery, KS1 and KS2 competition winners. 08/03/16 Prizes purchased and titivated, very impressive. Handed over to Jo Thuys in the meeting to take into school to be promoted in school assemblies. | Deborah Wilkinson | Completed | 2016-03-08
AP207 | 2016-01-12 | Confirmation of date for Quiz Night | Miss Ainsley to confirm which date quiz is scheduled for, 6th or 20th May. 20th is preferable for PTFA organisers. Miss Ainsley confirmed 20th, however Maria can no longer make this date, needs to revert to 6th. Miss Ainsley to check with School / Site Manager. Feb'16 Confirmation email that new date of 6th May agreed with school. | Miss Ainsley | Completed | 2016-02-01
AP208 | 2016-01-12 | Purchase Easter Egg for Whole-of-School | Natalie to source Cadbury’s Easter egg for each child at school, budget 75p. 08/03/16 Natalie confirmed 480 Cadbury Eggs purchased, identified that Busy Berries missed, is pursuing alternative option for this group of children. Claire Hale has volunteered to stick "purchased by the PTFA" labels on them. | Natalie Lockrey | Completed | 2016-03-01
AP209 | 2016-01-12 | Purchase Booklet or book mark true meaning of Easter | Deborah to source booklet or book mark about the true meaning of Easter, budget 25p. Suitable bookmark found 14p each, 500 required. Natalie to order on Deborah's behalf. 08/03/16 Bookmark's purchased, will be sent into school to be distributed with Easter Eggs. | Deborah Wilkinson | Completed | 2016-03-08
AP210 | 2016-02-03 | Disco Ticketing Co-ordinator | Dave confirmed that committee looking for someone to take on this responsibility. Jo Thuys to approach Clare Hale, before Dave makes contact via text / email. Claire Hale has been approached and happy to take on role. | Jo Thuys | Completed | 2016-03-08
AP211 | 2016-02-03 | Promotion of Summer Ball | Bex to include ticket details in next PTFA Newsletter. 08/03/16 Bex confirmed details included in newsletter, due out 10th March. Racheal has also promoted event on FB. | Bex Riddell | Completed | 2016-03-08
AP212 | 2016-02-03 | Advertise Summer Fayre Kick-Off Meeting | Bex to include ticket details in next PTFA Newsletter. 08/03/16 Bex confirmed details included in newsletter, due out 10th March. However, missed first meeting held on 8th. | Bex Riddell | Completed | 2016-03-08
AP213 | 2016-03-08 | Popcorn - allergies (suggestion to sell at Disco's) | Dave considering selling un sold Popcorn from Nursery event. Dave to include "allergy" . 17/05/16 as popcorn sold at Disco deemed acceptable. | Dave Rooney | Closed | 2016-05-17
AP214 | 2016-03-08 | Banner for Film Night | Agreed that Film Night should have a Banner (like other events) Bex to create "art-work", Michelle to speak to Andy ref making it for next event. 04/07/16 To be designed 13/09/16 Banner Made, put up ready for next film event | Michelle Dolphin / Bex Riddell | Completed | 2016-09-13
AP215 | 2016-03-08 | Test of Audio/Projector Equipment for film night. | Urgent Request that audio/projector equipment by tested and confirmation that this has been completed ASAP. 17/05/16 Testing completed, all working correctly | Miss Ainsley | Completed | 2016-05-17
AP216 | 2016-03-08 | Risk Assessment - Film Night | Risk Assessment to be completed, Dave to provide Disco RA as an example. Will include fire and first aid procedures. 17/05/16 Risk Assessment created, reviewed and issued. | Dave Rooney | Completed | 2016-05-17
AP217 | 2016-03-08 | Father's Day Hampers - Temporary Organisers required | Unfortunately Claire Paintain is not available to organise this event. Gemma & Ruth were suggested as possible volunteers (who helped with Mother's Day Hampers) who may be willing to share responsibility for delivering this event. Natalie to ask them. 17/05/16 Volunteers on-board. | Natalie Lockrey | Completed | 2016-05-17
AP218 | 2016-03-08 | Summer Ball Organisers | Committee to investigate if any volunteers willing to take on responsibility for organising next years SB. 17/05/16 Rachel was passed details of Alison Rooney and Louise Perry who may be interested. | Committee | Completed | 2016-05-17
AP219 | 2016-03-08 | DBS Checks | Agreed that as Lead Event Organisers Bex Riddell, Deborah Wilkinson and Dave Rooney should have a school related DBS check. Miss Ainsley to speak to school management team to see if they are willing to pay for these checks. 15/06/16 School have agreed to pay. 13/09/16 Only Dave Rooney's outstanding. Dave not present at the meeting so unable to establish progress. 17/01/17 Dave confirmed DBS check completed, certificate handed to school office | Dave Rooney | Completed | 2017-01-17
AP220 | 2016-03-08 | Pop-Up Banner for Yr. 6 Leavers Meal | Michelle advised that Andy could do a "pop-up" banner. Michelle to bring some additional information on sizes etc. Bex to create "art-work". Jul'16 To be designed Sep'16 made and used at Yr6 leavers event, very professional | Michelle Dolphin / Bex Riddell | Completed | 2016-09-13
AP221 | 2016-06-15 | Text Reminder - Fathers Day Hampers | Agreed to promote increase in donations, reminders necessary | Committee | Completed | 2016-07-05
AP222 | 2016-09-13 | Cadbury Selection Boxes | To investigate and report back to committee on best possible price of approx. 480 Cadbury selection boxes. Previously purchased for 70-80 pence each. Agreed that we should include Busy Berries. | Lisa / Deborah | Completed | 2016-11-19
AP223 | 2016-09-13 | Pantomime PTFA Volunteer Numbers | To confirm number of PTFA volunteers required by year group to accompany children to Christmas Panto. | Mrs Cullen | Completed | 2016-10-01
AP224 | 2016-09-13 | Casino Themed Summer Ball | To confirm that school have no objections to offering a casino themed night at Summer Ball. Reply from school would prefer not to use. | Mrs Cullen | Completed | 2016-11-01
AP225 | 2016-11-08 | Update of Charities Commission Website | Lisa to obtain personal details from the New Elected and Ordinary Members to enable the Charity Commission Website to be updated with the Trustee’s information. | Lisa Greenway | On-going | 2017-01-01
AP226 | 2017-01-17 | Lead Organiser - Mother's Day Hampers | Bex is currently waiting for a response from Claire Paintain to confirm if she is happy to organise this year | Bex Riddell | NEW | 2017-01-17
AP227 | 2017-01-17 | Decoration of Hampers | Deborah to pass boxes onto Debi Weller for decorating | Deborah Wilkinson | NEW | 2017-01-17
AP228 | 2017-01-17 | New Easter Egg Design for Colouring competition | A new design might inspire the children to participate. Committee to look for suitable replacement. Sonia, Lisa and Deborah all found suitable picture, however Deborah updated existing document with her picture - good to go. | Committee | Completed | 2017-01-17
AP228 | 2017-01-17 | Easter Egg Competition - Design | Agreed that new design might inspire the children to participate | Committee | NEW | 2017-01-17
AP229 | 2017-01-17 | Easter Egg Competition - 3 Egg Prizes | 3 Easter eggs to be purchased as prizes | Deborah Wilkinson | NEW | 2017-01-17
AP230 | 2017-01-17 | Purchase Individual Easter Eggs - WOS | Whole school to receive an individual egg – guide price £1 | Lisa Greenway | NEW | 2017-01-17
AP231 | 2017-01-17 | Confirm number of children in school for Easter Egg | Confirm number of children on register who can and cannot have chocolate and suggest suitable alternative | Mrs Cullen | NEW | 2017-01-17
AP232 | 2017-01-17 | Easter Bookmarks | Purchase individual bookmarks. Design and wording to be agreed and order placed. | Deborah Wilkinson | NEW | 2017-01-17
AP233 | 2017-01-17 | Additional promotional leaflets for Summer Ball | Kira advised that the number of tickets sold had not reached the threshold to make the event viable. Requested additional support to help promote event. | Bex Riddell | NEW | 2017-01-17
AP234 | 2017-01-17 | Annual Review of First Aid Bag | Lisa would complete an annual check for this school year however each lead organiser should be responsible for checking content in advance of their event. | Lisa Greenway | NEW | 2017-01-17